## Schedule
Project MVC Process Schedule | [11 empty] | TESTING
SI.NO | Module | Sub Module | Screens | Popup | Incharge | Planned Date |  | Actual Date |  | Status | % | Name | Planned Date |  | Actual Date |  | Status | %
[6 empty] | Start date | End date | Start date | End date |  |  |  | Start date | End date | Start date | End date
1 | Project | Project | Project Index |  | Anto | 2016-07-25 | 2016-07-25 |  |  | ○ | 100% | Sabari
2 |  |  | ProjectRegistration |  | Anto | 2016-08-01 | 2016-08-01 |  |  | ○ | 100% | Sabari
3 |  |  | BugListView |  | Anto | 2016-08-02 | 2016-08-02 |  |  | ○ | 100% | Sabari
4 |  |  | BugRegistration |  | Anto | 2016-08-02 | 2016-08-02 |  |  | ○ | 100% | Sabari
5 |  |  | BugView |  | Anto | 2016-08-03 | 2016-08-03 |  |  | ○ | 100% | Sabari
6 |  |  | BugEdit |  | Anto | 2016-08-03 | 2016-08-03 |  |  | ○ | 100% | Sabari
7 |  |  |  | BugFixed | Anto | 2016-08-04 | 2016-08-04 |  |  | ○ | 100% | Sabari
8 |  |  |  | BugIgnore | Anto | 2016-08-04 | 2016-08-04 |  |  | ○ | 100% | Sabari
9 |  |  | BugTypeRegistration |  | Anto | 2016-08-04 | 2016-08-04 |  |  | ○ | 100% | Sabari
10 |  |  |  | BugAdd | Anto | 2016-08-05 | 2016-08-05 |  |  | ○ | 100% | Sabari
11 |  |  |  | Ignore | Anto | 2016-08-08 | 2016-08-08 |  |  | ○ | 100% | Sabari
12 |  |  |  | DoubtRegister | Anto | 2016-08-09 | 2016-08-09 |  |  | ○ | 100% | Sabari
13 |  |  | AddListView |  | Anto | 2016-08-10 | 2016-08-10 |  |  | ○ | 100% | Sabari
14 |  |  | AddRegistration |  | Anto | 2016-08-11 | 2016-08-11 |  |  | ○ | 100% | Sabari
15 |  |  | ModuleDetailsindex |  | Anto | 2016-08-22 | 2016-08-25
16 |  |  | ModuleDetailsView |  | Anto | 2016-08-22 | 2016-08-25
17 |  |  | ModuleRegistration |  | Anto | 2016-08-22 | 2016-08-25
18 |  |  |  | MainModule | Anto | 2016-08-22 | 2016-08-25
19 |  |  |  | SubModule | Anto | 2016-08-22 | 2016-08-25
20
21
22 |  |  | DailyStatusView |  | Vignesh
23 |  |  | DailyStatusRegistration |  | Vignesh
24 |  |  | DownloadＤａｉｌｙＳｔａｔｕｓ
25 |  |  | TeamMembersNippoＶｉｅｗ |  | Vignesh | 2016-08-31 | 2016-08-31
26 |  |  | TechnicalStatusＶｉｅｗ |  | Vignesh | 2016-08-01 | 2016-08-01 |  |  | ○ | 100% | Sabari
27 |  |  | TechnicalStatusＲｅｇｉｓｔｅｒ |  | Vignesh | 2016-08-01 | 2016-08-01 |  |  | ○ | 100% | Sabari
28 |  |  | ReportView(MonthlyReportDetails) |  | Vignesh | 2016-08-02 | 2016-08-02 |  |  | ○ | 100% | Sabari
29 |  |  | ReportSingleView(TechnicalPerformance) |  | Vignesh | 2016-08-02 | 2016-08-02 |  |  | ○ | 100% | Sabari
30 |  |  | DownloadFullView(TechnicalPerformanceView)
31 |  |  | DownloadParticularView |  | Vignesh | 2016-08-02 | 2016-08-02 |  |  | ○ | 100% | Sabari
32
33
34
35 |  | Attendance | Attendance Index |  | SivaBalaji | 2016-08-17 | 2016-08-25 |  |  |  | 80% | Sabari
36
37
38 |  | Nippo | NippoIndex(DailyReportsView) |  | Anto | 2016-08-31 | 2016-09-01
39 |  |  | DailyReportRegistration |  | Anto | 2016-08-01 | 2016-08-02
39
40 |  | Experience | Experience index(experience list) |  | Sankar | 2016-08-08 | 2016-08-10 |  |  | ○ | 100% | Sabari
41 |  |  | Experience Registration |  | Sankar | 2016-08-11 | 2016-08-12 |  |  | ○ | 100% | Sabari
42 |  |  |  | Customer Name | Sankar | 2016-08-11 | 2016-08-12 |  |  | ○ | 100% | Sabari
43 |  |  |  | Incharge Name | Sankar | 2016-08-11 | 2016-08-12 |  |  | ○ | 100% | Sabari
44 |  |  |  | Programming Language | Sankar | 2016-08-11 | 2016-08-12 |  |  | ○ | 100% | Sabari
45 |  |  |  | Tool | Sankar | 2016-08-11 | 2016-08-12 |  |  | ○ | 100% | Sabari
46 |  |  |  | Data base | Sankar | 2016-08-11 | 2016-08-12 |  |  | ○ | 100% | Sabari
47 |  |  |  | Operating System | Sankar | 2016-08-11 | 2016-08-12 |  |  | ○ | 100% | Sabari
48 |  |  | ProjectView |  | Sankar | 2016-08-16 | 2016-08-17 |  |  | ○ | 100% | Sabari
49 |  |  |  | Project Description | Sankar | 2016-08-16 |  |  |  | ×
50 |  |  | Upload Experience List |  | Sankar | 2016-08-16 |  |  |  | ×
51 |  |  | Download Template |  | Sankar | 2016-08-16 |  |  |  | ○ | 100% | Sabari
52
53 |  | TimeSheetEntry | TimeSheetIndex(TimeSheetDetails) |  | Sankar
54 |  |  | UpdateTimesheet |  | Sankar
55 |  |  | DownloadTimesheet |  | Sankar
56 |  |  | OldTimeSheet |  | Sankar
57 |  |  | TimeSheetView |  | Sankar
58 |  |  |  | DownloadTimesheet | Sankar
59 |  |  | ExcelDownload(Timesheetview) |  | Sankar
60 |  |  | PDF download(timesheetview) |  | Sankar
61 |  |  | UpdateTimeSheet |  | Sankar
62 |  |  |  | DownloadTimeSheet | Sankar
63 |  |  | ExcelDownload(Timesheetview) |  | Sankar
64 |  |  | PDF download(timesheetview) |  | Sankar
65 |  |  | TimeSheetRegistration |  | Sankar
66
67
68
69
70
71 | Profile | MyProfile | MyProfileIndex |  | Anto
72 |  |  | PasswordChange |  | Anto
73 |  |  | ChangePicture |  | Anto
74 |  |  | FamilyDetailsUpdate |  | Anto
75
76 |  | House | HouseIndex |  | Sivajothi | 2016/8/
77
78
79 |  | Qualification | Qualification Index(EducationDetails) |  | Mathavan | 2016-08-19 | [5 empty] | Sabari
80 |  |  | EducationRegistration |  | Mathavan | 2016-08-19 | [5 empty] | Sabari
81 |  |  | Education Edit |  | Mathavan | 2016-08-19 | [5 empty] | Sabari
82
83 |  | Visa | VisaIndex |  | Vignesh | 2016-08-04 | 2016-08-04 |  |  | ○ | 100% | Sabari
84 |  |  | VisaRegistration |  | Vignesh | 2016-08-08 |  |  |  | × | 90% | Sabari
85 |  |  |  | VisaRegistration(webcam) | Vignesh | 2016-08-09 |  |  |  | × | 50% | Sabari
86 |  |  | VisaView |  | Vignesh | 2016-08-05 | 2016-08-05 |  |  | ○ | 100% | Sabari
87 |  |  | VisaEdit |  | Vignesh | 2016-08-08 |  |  |  | × | 70% | Sabari
88
89
90
91
92
93 |  | Certification | CertificationIndex(CertificationDetails) |  | Mathavan | 2016-08-17 |  |  |  | × |  | Sabari
94 |  |  | CertificationDetailsAdd |  | Mathavan | 2016-08-17 |  |  |  | × |  | Sabari
95 |  |  | JapaneseExamDetailView |  | Mathavan | 2016-08-17 |  |  |  | × |  | Sabari
96
97 |  | Bank | BankIndex(BankDetailsView) |  | Anto
98 |  |  | BankRegistration |  | Anto
99 |  |  |  | Bank details | Anto
100 |  |  |  | BranchName(BankDetails) | Anto
101 |  |  | BankAccountDetailsView |  | Anto
102
103
105 |  | Skills | SkillsIndex(SkillsDetails) |  | Mathavan
106 |  |  | SkillsRegistration |  | Mathavan
107 |  |  |  | Operating System | Mathavan
108 |  |  |  | Programming Language | Mathavan
109 |  |  |  | Data base | Mathavan
110 |  |  |  | Tool | Mathavan
111 |  |  |  | GUI | Mathavan
112 |  |  |  | WebServer | Mathavan
113 |  |  |  | MiddleWare | Mathavan
114 |  |  |  | WebTools | Mathavan
115 |  |  | SkillsEdit |  | Mathavan
116 |  |  | SkillsView |  | Mathavan
117
118 |  | Passport | PassportIndex(PassportDetails) |  | Sankar | 2016-08-19 | 2016-08-24
119 |  |  | PassportRegistration |  | Sankar | 2016-08-19 | 2016-08-24 |  |  |  | 75%
110 |  |  | PassportEdit |  | Sankar | 2016-08-19 | 2016-08-24 |  |  |  | 75%
111 |  |  | PassportView |  | Sankar
112
113
114 |  | LeaveForm | LeaveIndex |  | Sivabalaji | 2016-08-13 | 2016-08-16
115 |  |  | LeaveRegistration |  | Sivabalaji | 2016-08-13 | 2016-08-16
116
117
118 |  | Travel | TravelIndex |  | Mathavan | 2016-09-01 | 2016-08-02
119 |  |  | TravelRegistration |  | Mathavan | 2016-08-02 | 2016-08-03
120 |  |  | NewRequestRegistration |  | Sam | 2016-08-02 | 2016-08-03
121 |  |  | TravelRequest |  | Sam | 2016-08-03 | 2016-08-04
122 |  |  | TravelRequestDetails |  | Sam | 2016-08-03 | 2016-08-04
123
124 | Message | MessageList | MessageListIndex |  | Sabari | 2016-08-02 | 2016-08-11 |  |  | ○ | 100% | Sabari
125 |  |  | MessageView |  | Sabari | 2016-08-05 | 2016-08-09 |  |  | ○ | 100% | Sabari
126
| Test | Technical | TechinicalIndex(Trainingdetails) |  | mathavan | 2016-08-04 | 2016-08-05 |  |  | ○ | 100% | sabari
127 |  |  | TrainingDetailsView |  | mathavan | 2016-08-04 | 2016-08-05 |  |  | ○ | 100% | sabari
128 |  |  | TrainingResultView |  | mathavan | 2016-08-04 | 2016-08-05 |  |  | × | 50% | sabari
129
130 |  | Japanese | Japanese Index(Trainingdetails) |  | mathavan | 2016-08-08 | 2016-08-09 |  |  | ○ | 100% | sabari
131 |  |  | TrainingDetailsView |  | mathavan | 2016-08-08 | 2016-08-09 |  |  | ○ | 100% | sabari
132 |  |  | JapaneseResultView |  | mathavan | 2016-08-08 | 2016-08-09 |  |  | ○ | 100%
134
135 |  | Project | ProjectIndex(Trainingdetails) |  | mathavan | 2016-08-10 | 2016-08-11 |  |  | ○ | 100% | sabari
136 |  |  | TrainingDetailsView |  | mathavan | 2016-08-10 | 2016-08-11 |  |  | ○ | 100% | sabari
137 |  |  | TrainingResultView |  | mathavan | 2016-08-10 | 2016-08-11 |  |  | ○ | 100% | sabari
138 |  | JPnewTest | JPnewTest Index |  | mathavan | 2016-08-11 | 2016-08-11 |  |  | ○ | 100% | sabari
139 |  |  |  | TakeExam | mathavan | 2016-08-11 |  |  |  | ○ | 100% | sabari
141 |  |  | ResultView |  | mathavan | 2016-08-11 |  |  |  | ○ | 100% | sabari
142 | Points | Technical | TechnicalIndex |  | Vignesh | 2016-08-03 | 2016-08-03 |  |  | ○ | 100% | sabari
143 |  |  | PointsListView |  | Vignesh | 2016-08-03 | 2016-08-03 |  |  | ○ | 100% | sabari
144 |  |  | PointBigView |  | Vignesh | 2016-08-03 | 2016-08-03 |  |  | ○ | 100% | sabari
145 |  |  | PointParticularView |  | Vignesh | 2016-08-03 | 2016-08-03 |  |  | ○ | 100% | sabari
146 |  |  | ParticularView |  | Vignesh | 2016-08-03 | 2016-08-03 |  |  | ○ | 100% | sabari
147 |  |  | BugEdit
148 |  |  | BugDownload
150
151 |  | NonTechnical | NonTechnicalIndex |  | Vignesh | 2016-08-03 | 2016-08-03 |  |  | ○ | 100% | sabari
152 |  |  | PointsListView |  | Vignesh | 2016-08-03 | 2016-08-03 |  |  | ○ | 100% | sabari
153 |  |  | PointsBigView |  | Vignesh | 2016-08-03 | 2016-08-03 |  |  | ○ | 100% | sabari
154 |  |  | PointsParticularView |  | Vignesh | 2016-08-03 | 2016-08-03 |  |  | ○ | 100% | sabari
155 |  |  | ParticularView |  | Vignesh | 2016-08-03 | 2016-08-03 |  |  | ○ | 100% | sabari
156 |  |  | ParticularView(download)
157 | Documents | Document | DocumentIndex |  | Sivabalaji | 2016-08-26
158 |  |  | DocumentListView |  | Sivabalaji | 2016-08-26
159 |  |  | DocumentParticularView |  | Sivabalaji | 2016-08-26
160 |  |  | Download(ParticularViewDocuments) |  | Sivabalaji | 2016-08-26
161 |  |  | DocumentBigView |  | Sivabalaji | 2016-08-26
162
163
164 | Expenses | Travel | TravelIndex(LocalTravel) |  | Sam | 2016-08-22 | 2016/8/ |  |  | ○ | 100% | sabari
165 |  |  | LocalTravelRegistration |  | Sam | 2016-08-22 |  |  |  | ×
166 |  |  | LocalTravelUpdate |  | Sam |  |  |  |  | ×
167 |  |  | LocalTravelCopy |  | Sam |  |  |  |  | ×
168 |  |  | Download |  | Sam | 2016-08-22 | 2016/8/ |  |  | ○ | 100% | sabari
169
170 |  | Expenses | ExpensesIndex |  | Nambi | 2016-08-22 |  |  |  | ×
171 |  |  | ExpensesRegistration |  | Nambi |  |  |  |  | ×
172 |  |  | ExpensesUpdate |  | Nambi |  |  |  |  | ×
173 |  |  | ExpensesCopy |  | Nambi |  |  |  |  | ×
174
175 | Templates&Others | Template&others | Template&othersIndex |  | Sankar | 2016-08-02 | 2016-08-03 |  |  | ○ | 100% | sabari
176 |  |  | Download |  | Sankar | 2016-08-03 | 2016-08-05 |  |  | ○ | 100% | sabari
177
178
179 | SkypeClass | SkypeClass | SkypeClassIndex |  | SivaBalaji | 2016-08-09 | 2016-08-11 |  |  | ○ | 100% | sabari
180