## Schedule
Project MVC Process Schedule
SI.NO | Module | Sub Module | Screens | Popup | Incharge | Planned Date |  | Actual Date |  | Status | %
[6 empty] | Start date | End date | Start date | End date
1 | Project | Project | Project Index |  | Patturaj | 2016-05-28 | 2016-06-01 |  |  | ○ | 100%
2 |  |  |  | MB Employee Selection Popup | Patturaj | 2016-06-01 | 2016-06-02 |  |  | ○ | 100%
3 |  |  |  | SS Employee Selection popup | Patturaj | 2016-06-01 | 2016-06-02 |  |  | ○ | 100%
4 |  |  |  | Trainee Selection Popup | Patturaj | 2016-06-01 | 2016-06-02 |  |  | ○ | 100%
5 |  |  | Project Register & Edit |  | Daniel | 2016-06-01 | 2016-06-08 |  |  | ○ | 100%
6 |  |  |  | Customer Name selection popup | Daniel | 2016-06-08 | 2016-06-15 |  |  | ○ | 100%
7 |  |  |  | Programming Language Selection popup | Daniel | 2016-06-08 | 2016-06-15 |  |  | ○ | 100%
8 |  |  |  | Tools selection Popup | Daniel | 2016-06-08 | 2016-06-15 |  |  | ○ | 100%
9 |  |  |  | Database Selection popup | Daniel | 2016-06-08 | 2016-06-15 |  |  | ○ | 100%
10 |  |  |  | Operating System Selection popup | Daniel | 2016-06-08 | 2016-06-15 |  |  | ○ | 100%
11 |  |  | Project Details View |  | Madhavan | 2016-06-01 | 2016-06-03 |  |  | ○ | 100%
12 |  |  |  | Team Leader Selection Popup | Madhavan | 2016-06-06 | 2016-06-10 |  |  | ○ | 100%
13 |  |  | Project Report Details View(Daily Status)
14 |  |  | Attendance
15 |  |  | Feedback
16 |  | Module | Module Index |  | Siva Jothi | 2016-05-31 | 2016-06-02 |  |  | ○ | 100%
17 |  |  |  | Upload Module List Popup | Hari | 2016-06-20 | 2016-06-20 |  |  | ○ | 100%
18 |  |  |  | Upload Screen List Popup | Hari | 2016-06-20 | 2016-06-20 |  |  | ○ | 100%
19 |  |  |  | Download Module List Popup | Patturaj | 2016-06-22 | 2016-06-22
20 |  |  |  | Download Screen List Popup | Antony | 2016-06-22 | 2016-06-22
21 |  |  |  | Download Screen Details Popup | Antony | 2016-06-23 | 2016-06-23
22 |  |  | Module Register & Edit & Copy |  | Siva Jothi | 2016-05-03 | 2016-06-09 |  |  | ○ | 100%
23 |  |  | Module View |  | Siva Jothi | 2016-05-10 | 2016-06-14 |  |  | ○ | 100%
24 |  |  |  | Screen Selection Popup | Siva Jothi | 2016-05-15 | 2016-06-17 |  |  | ○ | 100%
25 |  |  |  | Employee Selection Popup | Antony | 2016-06-24 | 2016-06-27
26 |  |  | Screen View |  | Daniel | 2016-06-22 | 2016-06-23
27 |  |  | Module History |  | Siva Jothi | 2016-06-22 | 2016-06-24
28 |  | Bug | Bug index |  | Vignesh |  | 2016-06-21 |  |  | ○ | 90%
29 |  |  | Bug Register |  | Patturaj | 2016-06-08 | 2016-06-10 |  |  | ○ | 100%
30 |  |  |  | Incharge Name Selection Popup | Patturaj | 2016-06-10 | 2016-06-11 |  |  | ○ | 100%
31 |  |  | Bug details View |  | Vignesh | 2016-06-17 | 2016-06-21 |  |  | ○ | 100%
32 |  |  |  | Fixed Process Popup | Vignesh | 2016-06-17 | 2016-06-18 |  |  | ○ | 100%
33 |  |  |  | Ignore Process Popup | Vignesh | 2016-06-16 | 2016-06-18 |  |  | ○ | 100%
34 |  |  | Bug Type Register & Edit |  | Vignesh | 2016-06-22 | 2016-06-27 |  |  | × | 20%
35 |  |  | Bug Edit |  | Patturaj | 2016-06-20 | 2016-06-21 |  |  | ○ | 100%
36 |  |  |  | Incharge Name Selection Popup | Patturaj | 2016-06-10 | 2016-06-10 |  |  | ○ | 100%
37 |  | Add | Add List Index |  | Vignesh | 2016-06-01 | 2016-06-02 |  |  | ○ | 100%
38 |  |  | Add Register & Edit |  | Antony | 2016-06-09 | 2016-06-10 |  |  | ○ | 100%
39 |  |  |  | Incharge Name Selection Popup | Daniel | 2016-06-23 | 2016-06-23 |  |  | ○ | 100%
40 |  |  | Add details View |  | Antony | 2016-06-13 | 2016-06-14 |  |  | ○ | 100%
41 |  |  |  | Fixed Process Popup | Antony | 2016-06-15 | 2016-06-16 |  |  | ○ | 100%
42 |  |  |  | Ignore Process Popup | Antony | 2016-06-17 | 2016-06-20 |  |  | ○ | 100%
43 | Points | Technical | Index |  | Madhavan | 2016-06-22 | 2016-06-23
44 |  |  | Points Register and Edit |  | Madhavan | 2016-06-23 | 2016-06-24
45 |  |  | Points View |  | Hari | 2016-06-22 | 2016-06-22
46 |  |  |  | Add Points | Hari | 2016-06-23 | 2016-06-24
47 |  |  |  | Upload Keyword | Hari | 2016-06-27 | 2016-06-27
48 |  |  |  | Download latest keyword | Patturaj | 2016-06-23 | 2016-06-23
49 |  |  |  | Upload TestCase | Patturaj | 2016-06-24 | 2016-06-27
50 |  |  |  | Download Latest TestCase | Patturaj | 2016-06-28 | 2016-06-28
51 |  |  | Testcase BigView |  | Madhavan | 2016-06-24 | 2016-06-27
52 |  |  | Testcase view |  | Vignesh | 2016-06-29 | 2016-06-30
53 |  |  |  | Testcase Add popup | Daniel | 2016-06-24 | 2016-06-24
54 |  |  |  | Edit TestCase Content popup | Daniel | 2016-06-24 | 2016-06-27
55 |  |  |  | Copy TestCase popup | Daniel | 2016-06-27 | 2016-06-28
56 |  |  |  | Move TestCase popup | Daniel | 2016-06-28 | 2016-06-29
57 |  |  |  | Upload TestCase popup | Antony | 2016-06-27 | 2016-06-28
58 |  |  |  | Testcase Edit Popup | Antony | 2016-06-28 | 2016-06-29
59 |  |  | Testcase Detailed View |  | Madhavan | 2016-06-27 | 2016-06-28
60 |  | Non-Technical | Index |  | Daniel | 2016-06-29 | 2016-06-30
61 |  |  | Points Register and Edit
62 |  |  | Points View
63 |  |  |  | Add Points
64 |  |  |  | Upload Keyword
65 |  |  |  | Download latest keyword
66 |  |  |  | Upload TestCase
67 |  |  |  | Download TestCase
68 |  |  | All TestCase View
69 |  |  | Single TestCase View
70 |  |  |  | TestCase Edit Popup
71 |  |  |  | TestCase Copy Popup
72 |  |  |  | TestCase Move popup
73 |  |  |  | Upload TestCase popup
74 |  |  |  | TestCase Delete link
75 |  |  | TestCase Edit
76 |  |  | TestCase Add Popup
77 |  |  | Single TestCase Details View
78 | Project | Nippo | Daily report details(index) |  | Patturaj | 2016-06-29 | 2016-07-01
79 |  |  | Montly report details(history) |  | Daniel | 2016-07-01 | 2016-07-05
80 |  |  | Daily report details(view) |  | Hari | 2016-06-28 | 2016-06-29
81 |  |  | Daily report edit |  | Vignesh | 2016-06-30 | 2016-07-05
82 |  |  | Download monthly report details (xls) |  | Antony | 2016-06-29 | 2016-07-01
[5 empty] | Planned End Date |  | 2016-07-05